## Sistemi i vrojtimit te lejeve
SHTOJCA NR.12
SISTEMI I VROJTIMIT TE LEJEVE |  |  | FAZA I |  |  |  | FAZA II | [7 empty] | FAZA III
|  |  | KUSHTET NDERTIMORE |  |  |  | LEJE NDERTIMORE |  |  | PAGESAT DHE TAKSAT |  |  |  |  | INSPEKTIMI |  |  | CERTIFIKATA E PERDORIMIT
NUMRI I LENDES | EMRI I APLIKUESIT | KATEGORIA E NDERTIMIT I; II | KERKESA PER KUSHTE NDERTIMORE | PUBLIKIMI I KN | PERFUNDIMI I KOMENTEVE PUBLIKE | VENDIMI PER KN | KERKESA PER LEJE NDERTIMORE | SHQYRTIMI I TE GJITHA FAZAVE TE PROJEKTIT | VENDIMI PER LN | GABARITI I NDERTIMIT M2 | PAGESA PER LEJE | PAGESA PER RRITJE TE DENSITETIT | PAGESA PER INFRASTRUKTURE | MARREVESHJE ZHVILLIMORE (PO/JO) | INSPEKTIMI FILLESTAR | INSPEKTIMI I FAZAVE per KAT II | INSPEKTIMI PERFUNDIMTAR | KERKESA PER CERTIFIKATE TE PERDORIMIT | DATA E LESHIMIT

## Construction review process
Construction Permit Review Process Tracker
|  |  | STAGE I PERMIT REVIEW (if required) Terms of Construction |  |  |  | STAGE II PERMIT REVIEW Construction Permit |  |  |  | FEES & CHARGES |  |  |  |  | INSPECTIONS |  |  |  |  | OCCUPANCY CERTIFICATE
Permit No. | Name of the project | Category of Consruction (I, II, III) | Application for Terms of Construction Accepted | Public Notices Delivered & Posted | Public Comment Period Closed | Decision Issued | Application for Construction Permit Accepted | Compliance with Construction Terms | Code Compliance Review | Decision on Permit | No. of sq. meters | Permit Fee | Increased Density Fee | Infrastructure Fee | Development Agrement (Y/N) | Ist Inspections | Inspection of the structure | Inspection fo the installations | Fire Safety Inspections | Final Inspection | Application for Occupancy Certifcate Accepted | Date Issued
xxx-xxx-xxx | Sports Center |  | n/a | n/a | n/a | n/a | 17.02.13 | 18.02.13 | 21.02.13 | 10.03.13